## Est_Timeline
S.No. | Action Item | Description | Steps Involved | Start Date | End Date | Status
1 | Velero Project Documentation | Group Assignment/Project on Velero with below mentioned activities: | Tasks | 2022-03-15 | 2022-03-17 | Completed
Project Long Form
Project Short Form
Group Allocation
Timesheet
Issues and Risks
2 | Data Profiling | Using the Python profiling library, describe your understanding of the data | Download the data set and understand the set | 2022-03-18 | 2022-03-20 | Completed
|  |  | Load the data set into Jupyter notebook |  |  | Completed
|  |  | Profile data using Pandas and Numpy library (Describe, datatypes, formats, missing value checks, formatting checks, etc.) |  |  | Completed
3 | Data Wrangling and Cleansing | Using Pandas/Alteryx/XSV cleanse the data | Data Cleansing: Part-A 1. Filtering and aggregating if needed 2. Missing value handling | 2022-03-22 | 2022-03-31 | Completed
|  |  | Data Cleansing: Part-B 3. Deriving additional columns from existing datasets if needed 4. Cleaning (removing blank spaces, formatting dates, Capitalizing, etc.) | 2022-03-22 | 2022-03-31 | Completed
4 | Database Installation | Install NEO4J database | Install Neo4j Database is each team member machine | 2022-03-31 | 2022-03-31 | Completed
5 | Graph Database Design and Modeling | Design a graph database base on your understanding of the data in your file | Brainstorming of profiled and cleased data | 2022-04-01 | 2022-04-08 | Completed | CR in progress
Picking data itmes to be involved in database
|  | Prepare the Entity-Relationship diagram for the data | 1. Create ER diagram using draw.io 2. Create the relationship between entities in excel (Node-1, Node-2 and Relationship) | 2022-04-01 | 2022-04-08
6 | Data Mapping and Integration |  | Perform data mapping and Integration to your database for the entire dataset | 2022-04-09 | 2022-04-11 | Completed | CR in progress
Integrate the Neo4j database to the dataset
7 | Business and Technical Metadata | develop a business term list describing all the data elements available in the file | Prepare the metadata for business attributes( KBEs - What and why?) | 2022-04-12 | 2022-04-16 | Completed
Prepare the metadata for technical attributes( Fields - What and why?) Source, Target, Loadpatterns, Transformations etrc
8 | Data Validation and Data Visualization | using Python – Validate the data using python and provide a dashboard using python visualization libraries | Data Validation using Py libraries - Numpy and Pandas | 2022-04-17 | 2022-04-19 | Completed | Gauri - Assigned
|  |  | Data Visualization - Use matplotlib and plotly to create the visualization charts - Prepare the dashboard for project defined | 2022-04-20 | 2022-04-22 | Completed
Prepare unit test cases and perform Unit Testing
9 | System Integration (SIT) and User Acceptance Testing (UAT) | Test Cases – describe your validation & testing process |  | 2022-04-22 | 2022-04-24 | Completed
10 | Risks/Issues of the project |  | Identify and associated issues/risks | 2022-04-24 | 2022-04-25 | Completed
11 | Data Challenges and Resolution |  | Describe data challenges encountered and how you resolved them. | 2022-04-24 | 2022-04-25 | Completed
12 | Dashboard Presentation |  | Provide a full description of how to run your process 1. Database Creation and load 2. Visualization interpretation, describe information regarding your findings | 2022-04-25 | 2022-04-28 | Completed

## To_Do
S.No. | Task | Status
1 | Create technical metadata document | Completed
2 | Remove BLANKS from all the columns | Completed
3 | Change column names into Py script as per transformed data | Completed